## Sheet1
HNY CORE STANDARDS SELF ASSESSMENT PROCESS 24/25
Action | Notes | Timescale or Deadline
Evidence portal opened by | The ICB will use SharePoint, our existing portal for co-operation. Providers will be sent a link to the specific area for them to use. Evidence of newly "Green" core standards can be uploaded from this point onwards. | 31st July 2024 | Provider/ICB Activity
Existing Core Standards Support Meetings Continue* | These meetings have been taking place as BAU as the most efficient way of the ICB and the system seeking assurance of progression of core standards action plans; and allow for support and idea sharing. Some of these meetings have now been condensed to end in September. | 22nd July - 23rd September 2024 |  | Existing Core Standards Support Meetings*
Organisations to finalise first draft of core standards and submit to the ICB indicating their expected position by the end of October | Does not need to be signed off by the AEO. First draft for discussion in peer reviews. | 30th September 2024 |  | Domain | Date | Status
Provider Peer Review Meetings | ICB to facilitate 3 peer review meetings grouping providers together (Acute, Mental Health and Community). ICB's will also meet in October to peer review. | 1st-31st October 2024 |  | Governance | 2024-02-23 | Complete
Organisations to complete initial self-assessment and submit to ICB. | Final evidence of standards changed from Red or Amber to Green should have been uploaded to SharePoint. The Upload Portal will be opened in July and organisations can upload evidence from that point onwards should they wish to | By 31st October 2024 |  | Duty to Risk Assess | 2024-03-22 | Complete
ICB review submissions/provider meetings. Attendance should consist of EPRR Lead and AEO. | At this meeting providers should be prepared to discuss the evidence the have submitted for Green standards as per the above, but also where they are changing the compliance rating of any standard e.g. where a standard has gone from compliant to non, or partially compliant. If following the discussion, there is a difference in the provider organisations’ rating for a core standard and the ICB perception of what the rating should be, then the provider organisation is asked to provide details of this in their Board report on their core standards rating. | 1st-19th November 2024 |  | Duty to Maintain Plans | 2024-04-19 | Complete
LHRP Confirm and Challenge Meeting | Organisations and the ICB present their final core standards ratings to the HNY LHRP as normal. | 19th November 2024 |  | Command and Control | 2024-03-22 | Complete
ICB to submit report on system compliance | ICB to submit normal report on compliance of the system to NHS England Regional Team. | By 22nd November 2024 | ICB/Region Activity | Training and Exercising | 2024-06-18 | Complete
Regional team to undertake assurance process with ICBs on their submission and those of their providers | The regional team will then work with ICBs to obtain organisational level assurance ratings, and agree next steps to share learning and best practice ahead of the 2025/26 work programme being agreed | Between 25th and 29th November |  | Response | 2024-07-22 | Complete
RHRP Confirm and Challenge | HNY ICB will present the core standards ratings for HNY ICB and HNY Organisatrions at the NEY Regional Health Resilience Partnership (RHRP) as normal | By 2nd December 2024 |  | Warning and Informing + Co-operation | 2024-08-22 | Complete
Regional governance to take place - RHRP paper to regional management executive | No action required from ICBs or Providers | Between 3rd and 19th December 2024 | Regional/National Activity | Business Continuity and HAZMAT/CBRN | 2024-09-23 | Stood down
Regional paper to be submitted to the national team | No action required from ICBs or Providers | By no later than 20th December 2024
Deadline for ICBs and organisations to take their final self-assessment through Board. | Providers and ICBs ought to have taken their final assurance ratings through their own boards | By no later than 20th December 2025 | Provider/ICB Activity

## Sheet2
Existing Core Standards Support Meetings
Domain | Date | Status
Governance | 2024-02-23 | Complete
Duty to Risk Assess | 2024-03-22 | Complete
Duty to Maintain Plans | 2024-04-19 | Complete
Command and Control | 2024-03-22 | Complete
Training and Exercising | 2024-06-18 | Complete
Response | 2024-07-22 | To go ahead
Warning and Informing + Co-operation | 2024-08-22 | To go ahead
Business Continuity and HAZMAT/CBRN | 2024-09-23 | To go ahead